## LMS
[39 empty] | Gray |  |  | Not Completed
LMS Modernland Project Schedule | [8 empty] | Gantt Chart Learning Management System Modernland | [29 empty] | Green |  |  | Completed
Modernland Realty Tbk.
| Project Start Date | 2023-11-01 |  |  |  | Display Week | 23 |  | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30
| Project Lead | Tamara Tan | [6 empty] | 2024-04-01 | [6 empty] | 2024-04-08 | [6 empty] | 2024-04-15 | [6 empty] | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13 | [6 empty] | 2024-05-20
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2024-04-01 to 2024-05-26
[65 empty] | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | S | time axis 2024-04-01 to 2024-05-26
1 | Documentation |  |  |  | - |  |  | -
1.1 | Meeting Concept |  |  | 2023-11-01 | 2023-11-03 | 3 | 100% | 3
1.2 | BRD concept |  |  | 2023-11-06 | 2023-11-08 | 3 | 100% | 3
1.3 | Project Backgrouund |  |  | 2023-11-08 | 2023-11-14 | 7 | 100% | 5
1.4 | Business Pocess & Requrement Scope |  |  | 2023-11-15 | 2023-11-24 | 10 | 100% | 8
1.5 | Functional Requirements |  |  | 2023-11-24 | 2023-12-01 | 8 | 100% | 6
1.6 | Use Case Flow & Specification |  |  | 2023-12-01 | 2023-12-15 | 15 | 100% | 11
1.7 | User Activity Diagram |  |  | 2023-12-15 | 2023-12-27 | 13 | 100% | 9
1.8 | Data Architecture |  |  | 2023-12-27 | 2023-12-29 | 3 | 100% | 3
1.9 | User Interface Digitalization. |  |  | 2024-01-11 | 2024-01-19 | 9 | 100% | 7
2 | User Interface |  |  |  | - |  | * | -
2.1 | Brainstorming |  |  | 2024-01-01 | 2024-01-02 | 2 | 100% | 2
2.2 | Pengumpulan & Pembuatan Asset |  |  | 2024-01-05 | 2024-01-07 | 3 | 100% | 1
2.3 | Pembuatan Home Page & Login |  |  | 2024-01-08 | 2024-01-12 | 5 | 100% | 5
2.4 | Pembuatan mock-up Admin |  |  | 2024-01-27 | 2024-02-07 | 12 | 100% | 8
2.5 | Pembuatan mock-up user |  |  | 2024-02-08 | 2024-02-19 | 12 | 100% | 8
2.6 | Pembuatan mock-up HR & Admin |  |  | 2024-02-20 | 2024-02-29 | 10 | 100% | 8
2.7 | Finalisasi |  |  | 2024-03-01 | 2024-03-01 | 1 | 100% | 1
3 | Progamming |  |  |  | - |  |  | -
3.1 | Learning Boostrap & Framework |  |  | 2023-12-04 | 2023-12-07 | 4 | 100% | 4
3.2 | Pembuatan Portofolio |  |  | 2023-12-12 | 2023-12-23 | 12 | 100% | 9
3.3 | Pembuatan Resources |  |  | 2024-03-05 | 2024-03-14 | 10 | 100% | 8
3.4 | Pembuatan User Page |  |  | 2024-03-07 | 2024-03-26 | 20 | 100% | 14
3.5 | Pembuatan HR & Admin Page |  |  | 2024-03-26 | 2024-04-24 | 30 | 100% | 22
3.6 | Tambahan fitur User dari HR |  |  | 2024-05-27 | 2024-06-25 | 30 | 100% | 22
3.7 | Tambahan fitur HR dari HR |  |  | 2024-06-28 | 2024-07-26 | 29 | 100% | 21
3.8 | Testing Apps |  |  | 2024-07-26 | 2024-08-05 | 11 | 100% | 7
4 | [Task Category] |  |  | 2013-12-09 | 2013-12-09 |  |  | 1
4.1 | [Task] |  |  | 2013-12-10 | 2013-12-10 | 1 | 0% | 1
4.2 | [Task] |  |  | 2013-12-11 | 2013-12-11 | 1 | 0% | 1
4.3 | [Task] |  |  | 2013-12-12 | 2013-12-12 | 1 | 0% | 1
4.4 | [Task] |  |  | 2013-12-13 | 2013-12-13 | 1 | 0% | 1
4.5 | [Task] |  |  | 2013-12-14 | 2013-12-14 | 1 | 0% | 0
|  |  |  | 2013-12-15 | 2013-12-15 |  |  | 0
|  |  |  | 2013-12-16 | 2013-12-16 |  |  | 1
TEMPLATE ROWS |  |  |  | 2013-12-17 | 2013-12-17
See the Help worksheet to learn how to use these rows. You can hide these rows before printing. |  |  |  | 2013-12-18 | 2013-12-18
1 | [ Level 1 Task or Phase ] |  |  | 2013-12-19 | 2013-12-19 |  |  | 1
1.1 | . [ Level 2 Task ] |  |  | 2013-12-20 | 2013-12-20 |  |  | 1
1.1.1 | . . [ Level 3 Task ] |  |  | 2013-12-21 | 2013-12-21 |  |  | 0
1.1.1.1 | . . . [ Level 4 Task ] |  |  | 2013-12-22 | 2013-12-22 |  |  | 0
► Watch How to Create a Gantt Chart in Excel |  |  |  | 2013-12-23 | 2013-12-23
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## WBS Tree Diagram (hidden)
WORK BREAKDOWN STRUCTURE TREE DIAGRAM TEMPLATE
PROJECT TITLE | COMPANY NAME
PROJECT MANAGER | DATE
PROJECT TITLE
1 Activity Title
1.1 Task
1.2 Task
1.3 Task
1.1.1 Subtask
1.1.2 Subtask
1.1.3 Subtask
1.1.4 Subtask
1.1.5 Subtask
1.2.1 Subtask
1.2.2 Subtask
1.2.3 Subtask
1.2.4 Subtask
1.3.1 Subtask
1.3.2 Subtask
1.3.3 Subtask
2 Activity Title
2.1 Task
2.2 Task
2.3 Task
2.1.1 Subtask
2.1.2 Subtask
2.1.3 Subtask
2.1.4 Subtask
2.1.5 Subtask
2.2.1 Subtask
2.2.2 Subtask
2.2.3 Subtask
2.2.4 Subtask
2.3.1 Subtask
2.3.2 Subtask
2.3.3 Subtask
3 Activity Title
3.1 Task
3.2 Task
3.3 Task
3.1.1 Subtask
3.1.2 Subtask
3.1.3 Subtask
3.1.4 Subtask
3.1.5 Subtask
3.2.1 Subtask
3.2.2 Subtask
3.2.3 Subtask
3.2.4 Subtask
3.3.1 Subtask
3.3.2 Subtask
3.3.3 Subtask
4 Activity Title
4.1 Task
4.2 Task
4.3 Task
4.1.1 Subtask
4.1.2 Subtask
4.1.3 Subtask
4.1.4 Subtask
4.1.5 Subtask
4.2.1 Subtask
4.2.2 Subtask
4.2.3 Subtask
4.2.4 Subtask
4.3.1 Subtask
4.3.2 Subtask
4.3.3 Subtask

## WBS (hidden)
WBS Code | Task Name | Description | Start Date | End Date | Duration (days) | Resources
1 | Project Initiation
1.1 | Requirements Gathering | Collecting detailed requirements from stakeholders.
1.2 | Feasibility Study | Analyzing the feasibility of the project.
2 | Planning
2.1 | Project Plan | Developing a comprehensive project plan.
2.2 | Risk Assessment | Identifying and assessing potential risks.
3 | Execution
3.1 | Hardware Upgrade | Replacing outdated hardware components.
3.2 | Software Upgrade | Installing and configuring new software.
3.3 | Network Upgrade | Enhancing network infrastructure.
3.4 | Security Improvements | Implementing new security protocols and tools.
4 | Training
4.1 | User Training | Conducting training sessions for all staff.
5 | Monitoring & Control
5.1 | Performance Monitoring | Continuously monitoring system performance.
5.2 | Risk Management | Managing and mitigating risks throughout the project.
6 | Project Closure
6.1 | Final Review | Conducting a final review and assessment of the project.
6.2 | Documentation | Compiling all project documentation.
6.3 | Project Handover | Handing over the project deliverables to the stakeholders.